Million Veteran Program Overview

Questions

- Program Goals

- Target Number of participants

- How many of the million+ genomes that have been collected from veteran volunteers through the program for each year, with projection to reach the goal

- The annual number of genomes sequencing each year.

- Heard rumors that the program may have slowed down over the past year, is that accurate?  If so, was that part of the program plan or what caused that slow down?

- When is the collection expected to meet its target goal?

- How is the database being used for research

Program Goals

The overarching goal of the Million Veteran Program (MVP) is to enable personalized or precision care for all current and future generations of Veterans by incorporating genetic, lifestyle, military experience and exposure information to guide diagnosis, treatment and prevention of diseases and conditions, and improving their health and well-being.

Understanding how multiple factors interact and affect health requires analyzing data from very large numbers of people with and without a specific disease or health condition, as well as sophisticated analytic tools, including artificial intelligence, machine learning, natural language processing and statistical methods. Depending on the specific health condition, the specific population and how common or rare a genetic marker is, health and genetic data from hundreds of thousands to millions of Veterans of a specific population may be required.

Built on the foundations of trust and altruism of Veterans, and leveraging one of the best and most comprehensive electronic health records in the world, and world-class clinicians and researchers, MVP has enrolled over 1,070,000 participants to date.  MVP is conducting research in areas such as traumatic brain injury, PTSD, depression, suicide risk, tinnitus, Gulf War Illness, substance use disorders, cancer, heart disease and more. Importantly, MVP is working closely with the clinical operations in the VA to apply discoveries directly in the clinical care of Veterans. Some examples are:

- Early prediction of prostate cancer risk: A genetic risk score that can help predict risk for developing prostate cancer identified by MVP research is now being tested in a VA clinical trial that is comparing standard of care prostate cancer screening to standard of care plus the genetic risk score.

- Suicide prevention: Food insecurity and marital status were shown to increase risk of suicide identified by MVP research. These factors have been incorporated into VA’s suicide risk-prediction tool, REACHVET 2.0, which is set to be deployed in the VA in 2025.

- Ending Homelessness: MVP researchers in collaboration the Department of Energy applied artificial intelligence to develop a tool that can predict housing instability in Veterans 2 months in advance of the VA Homeless Screener survey response. Efforts are currently underway to validate these findings within the VA.

- Preventing end-stage kidney disease: A protective gene for end-stage kidney disease discovered by MVP is currently in a Pharma-sponsored clinical trial.

- Informing medication use based on genetics (Pharmacogenomics): MVP is partnering with the National Pharmacogenomics Program in the VA to inform treatment decisions based on genetics.

- Repurposing FDA-approved drugs to treat new health conditions: Efforts are underway to evaluate drug discovery, drug repurposing and drug safety using results from the largest genetic association study conducted in MVP.

- Launching MVP as a recruitment resource for genomics-informed clinical trials: Plans are underway to open up opportunities for Veterans enrolled in MVP to access clinical trials.

By expediting scientific discovery and generating knowledge from the blood specimens and data donated by Veterans, MVP will continue to inform and improve the delivery of care in the VA through new treatments, preventive strategies and biomarkers for early diagnosis.

Continuing enrollment of Veterans from all backgrounds, generations, deployments,  regardless of where they live, will continue to put Veterans first and provide real-world genomics data and discoveries to inform clinical care, even for rare health conditions.

Target Number of participants

An initial target of one million enrollees was established to assess number of people needed to successfully identify genetic risk factors for specific health conditions in specific populations.

Over the last few years, it became clear that significant focused efforts to ensure representation of populations of interest will be required to continue to inform clinical care in VHA and to ensure representation of the full Veteran population, including growing groups like women, younger Veterans, and Veterans from different racial and ethnic backgrounds, while remaining open to all Veterans.

As a result, through a strategic evaluation and planning process, MVP set target milestones for a subset of demographics and will continue to determine targets for additional subgroups of interest as need arises.

For example, while MVP has enrolled over 100,000 women Veterans to date, women are the fastest-growing Veteran segment and are projected to make up 18% or 2.2 million of the Veteran population by 2045. They also have distinct clinical care needs, and to best meet these needs, MVP has set a goal to increase enrollment of women Veterans to 200,000 by 2030 to match these demographic shifts. Similar efforts are underway to ensure continued enrollment other subpopulations of interest.

Additionally, the scale needed to make reliable discoveries that translate to improved clinical care across Veteran subgroups in VHA varies not only be demographics, but also health conditions. For many common, chronic diseases (e.g., heart disease, diabetes, mental health conditions), research requires hundreds of thousands to millions of participants to detect genetic risk factors to reliably inform clinical care. For rare diseases or ancestry-specific genetic variants, even larger, diverse cohorts and control groups are needed to ensure meaningful impacts to clinical care.

Targets will continue to be data-driven as Veteran’s clinical needs evolve. Without continued enrollment, VA risks missing critical genetic factors that can have a direct impact on clinical care. This will ensure every Veteran has the opportunity to benefit from the VA clinical care innovations that MVP enables.

How many of the million+ genomes that have been collected from veteran volunteers through the program for each year, with projection to reach the goal

Blood specimens have been collected from over 1,000,000 Veteran participants of the MVP. To date, over 200,000 of the MVP specimens have undergone whole genome sequence (WGS) analysis.

A goal of sequencing every MVP participant or even 1M MVP samples will depend on many factors, including VHA budget priorities and sequencing costs. At the FY24 rate, 1M WGS will be completed in FY2080. At the accelerated FY19-20 rate, we could hit that target in a little over 12 years - FY2038.

Total number of MVP enrollment, blood specimens collected, genotyped and whole genome sequenced by fiscal year (FY) are shown in the table below.

|  | Total Enrollments | Total Specimens Collected | Genotyped Samples | Whole Genome Sequencing |
| --- | --- | --- | --- | --- |
| FY11 | 7,083 | 7,056 | - | - |
| FY12 | 87,998 | 87,532 | - | - |
| FY13 | 112,268 | 111,089 | - | - |
| ,FY14 | 105,446 | 104,605 | 207,806 | - |
| FY15 | 103,252 | 102,528 | 197,709 | 129 |
| FY16 | 99,763 | 95,929 | 107,161 | 106 |
| FY17 | 90,344 | 89,058 | 86,456 | 3,154 |
| FY18 | 96,854 | 93,525 | 77,989 | 9,240 |
| FY19 | 88,002 | 84,607 | 83,444 | 63,520 |
| FY20 | 39,339 | 33,171 | 8,569 | 65,609 |
| FY21 | 22,392 | 16,383 | 16,937 | 6,445 |
| FY22 | 55,799 | 45,045 | 45,402 | 9,976 |
| FY23 | 73,647 | 59,824 | 64,101 | 23,049 |
| FY24 | 63,208 | 52,190 | 92,342 | 14,400 |
| FY25 to date | 24,858 | 22,600 | 11,246 | 5760 |
| TOTAL | 1,070,253 | 1,005,142 | 999,162 | 201,388 |

Heard rumors that the program may have slowed down over the past year, is that accurate?  If so, was that part of the program plan or what caused that slow down?

The program balances competing goals that are prioritized within fixed budget and personnel resources. These include cohort maintenance, cohort expansion, health data (phenomic) and molecular data expansion, supporting researcher access to the resource and supporting clinical activities. Following enrollment of the millionth participant, MVP slowed recruitment activities (including mailed invitations and email campaigns) to allow for:

- Shifting of resources to data expansion including military exposures and mental health data and increasing access for researchers to accelerate clinical impact for Veterans.

- Development of refreshed recruitment materials including focused recruitment targets and strategies based on Veteran feedback

- Reconciliation of specimens to obtain blood from as many MVP participants as possible

- Review of internal processes and procedures for streamlined and enhanced program administration

- Enhanced MVP Online user interface and user experience to support driving more enrollment to the online platform and shifting some staffing resources to other activities.

- When is the collection expected to meet its target goal?

As MVP does not have an overarching end goal for enrollment to keep the program relevant to todays and tomorrow’s Veterans, it is expected that enrollment would continue indefinitely. Enrollment targets will continue to be evaluated and adjusted based on Veteran and VHA clinical needs and evolving demographics. To keep the cohort vital and up-to-date, we also need to collect new data from participants such as military exposure to increase the utility for clinical care.

- How is the database being used for research?

Approved VA researchers access coded genetic, electronic health record, and survey data from MVP participants behind the VA firewall in the MVP scientific computing environment, Genisis and the associated VA Enterprise Cloud, where all the required analytic tools are provided. When combined, these data are used to investigate the impacts of genes, lifestyle, and exposures on health conditions important to Veterans and relevant discoveries advanced to inform VHA clinical care.

- Currently, direct access to individual level MVP data is only available to approved VA-affiliated researchers, but we’re working on ways to expand secure access to a broader group of researchers and allow for even more discoveries.

- Access to aggregate data and summary statistics from studies using MVP data are available in the NIH National Library of Medicine dbGaP resource to facilitate sharing with the broad research community.