## Slide 1: Research Enterprise Initiative Report-Out: Session 1
August 17, 2022
1
Notes: Rachel to Present
Good afternoon and welcome to the first session of the Research Enterprise Report-Out Sessions
Today, we will be reviewing the progress and next steps of each of the initiatives we launched last year as part of the Research Enterprise Transformation.
These meetings will help ORD Leadership determine the next steps and future of the broader Research Enterprise Transformation.
[Rachel to share any other applicable thoughts or recommendations regarding these meetings]

## Slide 2
* Initiative Executive Sponsors are the first name listed for each initiative above; initiative owners are the second name
Session 1 ORD Strategy & Internal Organization Initiatives
8/17, 1:30 – 2:30 PM:
(5 mins) Introduction: Rachel Ramoni
(15 mins) Org Alignment: Rachel Ramoni & Molly Klote
(15 mins) AMP: Chris Bever & Ken Myrie
(5 mins) STEAM: Wendy Tenhula & Eva-Marie Austin
(5 mins) Finance Process: Wendy Tenhula & Jason Berlow
(10 mins) Discussion
(5 mins) Decisions and Action Items
Session 2 Field Support Initiatives
8/19, 1:00 – 2:00 PM:
(5 mins) Introduction: Rachel Ramoni
(20 mins) IT & Data Governance: Molly Klote & Scott DuVall
(5 mins) FERSS: Grant Huang & Tony Laracuente
(5 mins) Central Research HR: Grant Huang & Tony Laracuente
(5 mins) PRP: Grant Huang & Krissa Caroff
(10 mins) Discussion
(5 mins) Decisions and Action Items
Report-Out Schedule
Notes: Rachel to Present
During the first session, myself, Chris, and Wendy will present on the initiative that each of us sponsor.
During the second session, Grant and Molly will present on their initiatives.
I will start out by presenting on the Organizational Alignment initiative.

## Slide 3: Organizational Alignment
3

## Slide 4: Organizational Alignment: Objectives
Initiative Objectives: | Ensure alignment of organizational structure and roles with the desired enterprise functions to build capacity and better support researchers, Veterans, and the broader VA Research Enterprise
Major Outputs Promised: | Design principles and standards Official org chart compared with real-world scope of control analysis L1 & L2 org chart, role charters, decision rights L3-L5 org chart, role charters, decision rights Communications plan All new signed org chart and position descriptions
4

## Slide 5: Organizational Alignment: Delivery Status
Outputs Delivered: | Design principles and standards; official org chart compared with real-world scope of control analysis; L1 & L2 org chart, role charters, decision rights; Communications plan; Compiled org charts reflecting Oct 1 changes; DEAN’s Concurrence Form signature for Oct 1 changes
Outputs Rescheduled: | L3-L5 org chart, decision rights, end-state signed org chart
Lessons Learned: | Decided to shift to phased roll-out approach to allow for learning from prototypes and additional opportunities to have stakeholder participation. This created a major shift away from fully designing the organization by Oct 1.
Current Roadblocks: | No currently identified roadblocks
Mitigation Strategies: | N/A
5

## Slide 6: Organizational Alignment: Proposed Next Steps
Recommendations for Initiative in FY23: | Based upon the approximate 2-year timeline announced in June, org alignment should be fully completed by October 1, 2024. By Dec 31, 2022, we should have a firm timeline for the remainder of the phases and what they will entail. (Including but not limited to, Chris must decide how and when we will phase in the new RFA, review, and award process.) Ensure that resources are in place to support the transition to the new RFA, submission, review, and award process, for example, training, communication, help desk, adjustments in eRA Commons, etc. Identify enterprise centers that will not need to compete for funding and create a plan to establish them. During Phase 2 (Proposed: Oct 1, 2022 to April 1, 2023), establish final form of reporting to L1 (all final L2s established, no other parties reporting to L1, and all non-L1 functions are being conducted by an L2). Create a plan to document standard operating procedures for ORD and begin documenting those that have been established. Ensure that all known, and newly identified ORD functions and activities have an L2 accountable party and a plan for a responsible party.
6

## Slide 7: Organizational Alignment: Proposed Phased Implementation Timeline
Proposed Phased Implementation Timeline: | 
7
Phase | Start date | End date | Duration
Phase 1: | ~May 1, 2022 | Oct 1, 2022 | 5-months
Phase 2: | Oct 2, 2022 | April 1, 2023 | 6-months
Phase 3: | April 2, 2023 | Oct 1, 2023 | 6-months
Phase 4: | Oct 2, 2023 | Oct 1, 2024 | 1-year

## Slide 8: Organizational Alignment: Proposed Next Steps
Major FY23 Outputs: | Timeline for remaining phases. Plan for transition from existing RFA, submission, review, and funding model to new model. Resource needs to transition from existing processes including but not limited to RFA, submission, review, and funding model to a new model. L1 reporting structure in final form. Plan for enterprise centers. Identification and assignment of critical functions and activities (some may need to be piloted or tested) Implementation of selected functions, activities, and necessary change management (feedback/focus groups/workgroups/etc.) Publish ORD standard operating procedures Plan for and successfully executed change management activities
Immediate Next Steps: | Identify and document known functions and activities for ORD at this time and ensure that they have an L2 assigned. Between now and December 2022, each L2 will define their organizational alignment activities for each phase based on the proposed phased implementation timeline.
ORD Leadership Support Required to Accomplish Initiative Objective: | Proactive engagement between L2s to complete FY23 outputs. Proactive engagement by L2s to involve staff in completing FY23 outputs.
8

## Slide 9: Actively Managed Portfolios
9

## Slide 10: Actively Managed Portfolio: Objectives
10
Initiative Objective: Provide research leaders with the autonomy and tools to enhance communication, coordination, and collaboration with clinical partners to enable a more rapid response to research priorities focused on the unique health challenges faced by Veterans.
This will be accomplished through the following actions:
Define the requirements, capabilities, processes, and resources that comprise an Actively Managed Portfolio (informed by the Learning Health System model)
Develop a plan to increase the maturity of the Precision Oncology Portfolio as an AMP​ in order to serve as a model and establish the Standard Operating Procedures and structures for other portfolios
Establish key performance indicators for Actively Managed Portfolios to track and evaluate the efficacy of research projects and the performance of an Actively Managed Portfolio​ against its critical goals
Coordinate and prioritize funding for research projects within an AMP by:
Establishing standard operating procedures for how an AMP lead will coordinate ORD funded projects and funding decisions within their purview
Developing standard operating procedures for rapid and program-directed peer review of proposals, when such approaches are necessary to meet AMP performance targets

## Slide 11: Actively Managed Portfolio: Objectives
Outputs Listed: | AMP Charter AMP Leader Role Charter Gap Analysis of P.O. Communications Framework Change Champion materials P.O. Prioritized Action Plan AMP funding decision SOPs SOPs for rapid and program-directed peer reviews and funding Inventory of needed dashboard functionality with PA Team P.O. funding autonomy Codified performance metrics to measure an AMP Portfolio Analysis Dashboard AMP progress reports on objective accomplishments
11

## Slide 12: Actively Managed Portfolio: Delivery Status
Outputs Delivered: | AMP Charter AMP Leader Role Charter Gap Analysis of P.O. Communications Framework Change Champion materials SOPs for rapid and program-directed peer reviews and funding (In Process) P.O. Prioritized Action Plan (In Process) Inventory of needed dashboard functionality with PA Team Portfolio Analysis Dashboard (By EOFY 22)
Outputs Rescheduled: | Still Planned But Delayed (FY 23) AMP budget decision SOPs Codified performance metrics to measure an AMP
12

## Slide 13: Actively Managed Portfolio: Delivery Status
Lessons Learned: | The underlying structure that supports the review process presents challenges to developing and implementing accelerated reviews as extensions of the already existing process.
Current Roadblocks: | There are no significant strategic roadblocks hindering completion of the initiative Tactical challenges which will be addressed as AMP continues in development: IC Codes, eRA, RAFT Flexibility with systems like eRA is a challenge RAFT changes cannot occur quickly Working with existing systems to maintain compliance as prototype launches and operates The current review systems are not flexible/nimble enough in supporting a prototype AMP that utilizes standard merit review process and accelerated review processes. This presents challenges to integration of processes already firmly in place throughout the enterprise
Mitigation Strategies: | PO AMP will work with administrators to overcome these challenges Prototype implementation is on track and continuing planned work will be addressed in FY 23 PO AMP will continue building on its iterative design model to preserve successful initiative components, phase out elements as necessary, and introduce additional opportunities for high operational performance
13

## Slide 14: Actively Managed Portfolio: Proposed Next Steps
Recommendation for Initiative in FY23: | Carry on with original objectives on extended timeline
Major FY23 Outputs: | Performance metrics developed as AMP matures over first-year of operations Develop feedback mechanisms and formal evaluation criteria Identify and launch at least 1 additional prototype AMP Develop criteria/playbook for establishing additional AMPs Formalize feedback/iterations of prototypes Revise and update AMP Charters as necessary based on learnings
14

## Slide 15: Actively Managed Portfolio: Proposed Next Steps
Immediate Next Steps: | Finalize policies for prototype implementation on 1 Oct 22 Develop LOI template (input from ORPPE&E), RFA(s) Continue Research Roadmap development with 1 Oct 22 target for prototype implementation Plan and test initial research case through PO AMP Meet with Director of IRB network (Don Workman) and Chief Veterinary Medical Officer (George Lathrop) to discuss process improvements for accelerated reviews
ORD Leadership Support Required to Accomplish Initiative Objective: | Approval of contract staff support for AMP accelerated reviews Establish whether AMPs have a separate budget and, if so, how that is determined
15

## Slide 16: Finance Process
16

## Slide 17: Finance Process: Objectives
Initiative Objectives: | Maximize the impact of VA research funding by establishing standardized, transparent processes for allocating, obligating, and expending ORD funds
Outputs Listed: | 
17
Deliverable | Status
Stakeholder Interviews and Findings | Delivered
Monthly Training Topics and Cadence for FY22 | Delivered
Monthly Training sessions: 4 (As of July, 2022) | Delivered
Field Survey Analysis | Delivered
Quarterly Thematic Training Outline for FY 23 | Delivered
Monthly Training Plan FY 23 | Delivered
Process Map: RAFT | Delivered
Policy on Carryover by Field by Q1 (Memo) | Rescheduled (September2022)
SOP: Reallocation | Delivered V1 (Rescheduled for Implementation in FY 23)
Framework and Criteria for Reallocation | Delivered V1 (Rescheduled for Implementation in FY 23)
Score Card for Proposal Review | Delivered V1 (Rescheduled for Implementation in FY 23)
Best Practice Documentation Template | Delivered
Best Practice Documents – 3 Topics | Rescheduled (September 2022)
Share Point Centralized Landing Page | Rescheduled (September 2022)
Finance Communication Plan | Rescheduled (September 2022)
Notes: Notes: The table shows the outputs that have been developed, delivered and rescheduled as a part of Initiative Objectives until July, 2022. The tasks pertaining to Objectives 3 & 4 regarding reallocation criteria and processes have gone through initial phase of development (May-July) but were rescheduled to be further developed in FY 23 to maintain priority on trainings and best practices that were determined as a critical foundational steps to enable further changes.

## Slide 18: Finance Process: Delivery Status
Outputs Delivered: | Stakeholder Interviews and Findings, Monthly Training Topics and Cadence for FY22, Q2 RAFT Data Analysis, Monthly Training sessions: 4 (As of July 2022), Field Survey Analysis, Quarterly Thematic Training Outline for FY 23, Monthly Training Plan FY 23, Process Maps: Reallocation; RAFT; PMO; Pull Backs, SOP: Reallocation, Framework and Criteria for Reallocation, Score Card for Proposal Review, Best Practice Documentation Template, Outlines for Best Practice Documentation
Outputs Rescheduled: | SOP: Reallocation, Framework and Criteria for Reallocation, Score Card for Proposal Review (Rescheduled for FY 23), Landing Page, Communication Plan, Best Practice Documentation Outputs supporting Objectives 3 & 4 have been drafted and delivered for review. But the implementation of these deliverables has been postponed to FY 23 as the initiative owner has determined that the current needs of field trainings along with best practice documentation are critical and need to be strategically prioritized to enable the successful implementation of these outputs. These deliverables will be further developed in FY 23 for implementation.
Lessons Learned: | We have discovered during development that training programs play a critical role in successfully implementing all the five objectives of finance initiative. In order to establish effective and efficient financial processes at the stations to allocate and obligate funds in a timely manner, field staff need to be empowered with knowledge on policies, procedures, systems and tools through foundational trainings.
Current Roadblocks: | None (Challenges: Bandwidth of Initiative team to contribute to initiative workload and identifying the field SMEs to develop best practices)
Mitigation Strategies: | We are continuing to monitor feedback from the trainings, as participation and buy-in from the field is critical to success. We have been involving the initiative team in the development process and maintaining clear lines of communication to accommodate any changes and additional requests. As a part of maintain clear lines of communication, we have planned to establish centralized landing page in SharePoint by end of August 2022 to organize and communicate information with the field stakeholders. We are mitigating the risk of noncompliance or lack of buy-in with our recommendations for trainings, best practice documentation, communication plans by gathering constant feedback from the initiative team and following an iterative approach to development of training plans and streamlined process documentation.
18
Notes: Trainings, best practice documentation and communications have been the primary focus in FY 22 as the initiative team has determined that the field staff need to be empowered with knowledge on policies, procedures, systems and tools through foundational trainings prior to developing and implementing the complex tools of reallocation. So, the tasks pertaining to Obj 3&4 have been rescheduled for further development and testing in FY 23 to maximize the impact.

## Slide 19: Finance Process: Proposed Next Steps
Recommendation for Initiative in FY23: | Prioritization of FY 22 Objectives 3 & 4 in FY 23​ Integrating budget execution/formulation processes​ Ensuring ORD- and VHA-level policy alignment on issues impacting local finance stakeholders​ Improving operations under financial uncertainty, like Continuing Resolutions​
Major FY23 Outputs: | Trainings; Formalized Reallocation processes; Streamlined Operations-PMOs and Pull Backs; Communication Plan with tools-Centralized Landing Page; Best Practice Documentation
Immediate Next Steps: | List of immediate next steps initiative will take based on: Maintain clear lines of communication between Field and VA ORD Finance through development of Best practice documentations and Centralized landing page Continue Monthly Trainings and make updates to trainings as per feedback from field survey Draft policies for field implementation in FY 2023 Develop policy on 4% Carryover Prioritization of Objectives 3 & 4 Establishing objectives for FY 23
ORD Leadership Support Required to Accomplish Initiative Objective: | Leadership has provided support at the right level to implement the finance objectives.
19
Notes: The next steps for remainder of FY 22 include continuation of trainings, building best practice documentation with initiative team and communicating these resources to the field. One of important steps include drafting a policy on 4% Carry over based on the memo from PY to increase compliance to obligation of funds by the field by end of FY. To prepare for FY23, initiative team has begun working on developing and strategically prioritizing objectives based on field feedback through survey and initiative team insights for FY 23.

## Slide 20: Staff Training Empowerment and Motivation
20

## Slide 21: STEAM: Objectives
Initiative Objectives: | Implement effective leadership practices across ORD and help with career development for all staff
Outputs Listed: | In Phase 3: Formalization (July 22 – September 22) of Five-Phase Roadmap Proposed: Formalization of plan, timelines, and committed resources Contract awarded (if applicable) Actual: Plan, timeline, resources: Statement of Work and Financial Docs – reviewed by OGC OPM and VA need to agree on recommended OGC revisions
21
Notes: STEAM developed objectives:
Increase access to leadership and team development training
Build skill development around:
    Leadership
    Communication
    Team Building
    Growth
    Future of Work
Cultivate a staff that feels empowered, valued, and able to apply their enhanced skills

## Slide 22: STEAM: Delivery Status
Outputs Delivered: | Phase I Data Collection and Scope Phase II Resource Development Phase III Formalization (in-process)
Outputs Undelivered: | None - Aim is to have Statement of Work (SOW) and 7600 Finance Documents signed by OPM and VA by End of Fiscal Year 2022
Lessons Learned: | Sustain: Resource Allocation (i.e. budget) Weekly meeting cadence – rapid succession generated ideas for vision and scope Diversity of workgroup Focus interviews – provided relevant/validating feedback Opportunity for Growth: Sustainment beyond FY 25/26 Offerings/participation beyond ORD staff Visibility/accountability of previous leadership trainings for individuals – opportunity to share
Current Roadblocks: | Post-legal review requires revised SOW and 7600s for both agencies, risk of further delay, yet still slated for FY23 start
Mitigation Strategies: | Rapid and transparent engagement with Finance, OGC, OPM, and STEAM for finalized product
22

## Slide 23: STEAM: Proposed Next Steps
Recommendation for Initiative in FY23: | Period of Performance for Option Year 1: Oct 1, 2022 – Sep 30, 2023 Timelines for courses established and courses scheduled for FY23 Launch OPM-sponsored long-term success metrics plan for 3-9 months post-course impact
Major FY23 Outputs: | Half-day and two-day courses underway Application screening for Regional Leadership Development Program (RLDP) participants Start RLDP (6 months)
Immediate Next Steps: | OPM and VA agree on revised SOW – pre-signatures SOW signed by both agencies; funds obligated First two courses scheduled for FY23 Q1
ORD Leadership Support Required to Accomplish Initiative Objective: | Managers and Supervisors to support protected time for employees to participate Financial resources committed for courses – please ensure staff participation so a slot does not go unused
23

## Slide 24: Research Enterprise Initiative Report-Out: Session 2
August 19, 2022
24
Notes: Rachel to Present
Good afternoon and welcome to the second session of the Research Enterprise Report-Out Sessions
Today, we will be reviewing the progress and next steps of each of the initiatives we launched last year as part of the Research Enterprise Transformation.
These meetings will help ORD Leadership determine the next steps and future of the broader Research Enterprise Transformation.
[Rachel to share any other applicable thoughts or recommendations regarding these meetings]

## Slide 25
* Initiative Executive Sponsors are the first name listed for each initiative above; initiative owners are the second name
Session 1 ORD Strategy & Internal Organization Initiatives
8/17, 1:30 – 2:30 PM:
(5 mins) Introduction: Rachel Ramoni
(15 mins) Org Alignment: Rachel Ramoni & Molly Klote
(15 mins) AMP: Chris Bever & Ken Myrie
(5 mins) STEAM: Wendy Tenhula & Eva-Marie Austin
(5 mins) Finance Process: Wendy Tenhula & Jason Berlow
(10 mins) Discussion
(5 mins) Decisions and Action Items
Session 2 Field Support Initiatives
8/19, 1:00 – 2:00 PM:
(5 mins) Introduction: Rachel Ramoni
(20 mins) IT & Data Governance: Molly Klote & Scott DuVall
(5 mins) FERSS: Grant Huang & Tony Laracuente
(5 mins) Central Research HR: Grant Huang & Tony Laracuente
(5 mins) PRP: Grant Huang & Krissa Caroff
(10 mins) Discussion
(5 mins) Decisions and Action Items
Report-Out Schedule
Notes: Rachel to Present
During the second session, Grant and Molly will present on the initiatives they sponsor.

## Slide 26: IT & Data Governance
26

## Slide 27: IT & Data Governance: Objectives
Initiative Background: | VA has some of the most complex and comprehensive medical record data in the world. Research has a critical dependency on IT and data systems that are often funded through a separate appropriation. To accomplish particular projects or types of research, ORD and other groups have built specialized systems within these resource constraints. For the VA to maintain its position at the forefront of scientific discovery, strategy and oversight are needed to align resources, organize systems, and standardize processes supporting research. The initiative will establish a centralized system of systems to increase capabilities and resources for researchers to efficiently and effectively conduct research to meet the needs of Veterans.
Goals and Objectives : | ORD has governance over a modernized, secure, collaborative system-of-systems with associated processes that increase capability and access for ORD staff and researchers to efficiently conduct and support research. ORD will develop and implement a strategic plan to organize the systems and their components across the research enterprise, which aligns with current and forecasted resources, policies, and ORD’s strategic priorities. ORD will establish Standard Operating Procedures (SOP) to support current policies and systems for both IT and Data, that ensure services and products are delivered consistently every time across the research enterprise. ORD will establish IT and Data Governance to provide policy, strategy, best practices, coordination, and standards aligned with the VA and VHA Data Management Strategy.
27

## Slide 28: IT & Data Governance: Delivery Status
Outputs Delivered: | Initial assessment of IT resources (interviews of system owners and system SMEs). Selected set of system resource maps. Established a System Owner Committee (SOC) to share information and lay groundwork for governance through the development of business requirements.
Outputs Rescheduled: | Develop and implement a strategic plan to organize the systems and their components across the research enterprise, which aligns with current and forecasted resources, policies, and ORD’s strategic priorities. Establish Standard Operating Procedures (SOP) to support current policies and systems for both IT and Data, that ensure services and products are delivered consistently every time across the research enterprise. Establish IT and Data Governance to provide policy, strategy, best practices, coordination, and standards aligned with the VA and VHA Data Management Strategy.
Lessons Learned: | Stakeholders' willingness and time allocated to contribute to this initiative presumably connected to incentive structure based on position, interests, and perceived impact to their research. Nature of ORD's IT and data is even more extensive, decentralized, and difficult to reveal than anticipated.
Current Roadblocks: | Personnel shortages
Mitigation Strategies: | Leverage Rios team to apply lessons learned from initial inventory to complete the inventory work. Focus on the deliverables.
28
Notes: While increasing awareness of the IT and data environment to support the strategic plan, we shifted some focus to operational line of effort to take opportunity to increase compute capabilities and data repository capacity that more immediately affects research. Moved other SOPs and governance activities to after delivering strategic plan that which will include a set of more informed, actionable items for these elements.

## Slide 29: IT & Data Governance: Proposed Next Steps
Recommendation for Initiative in FY23: | The team continues forward progress along the strategic line of effort developing the strategic plan after finishing the capability (gap) analysis in Dec-2022.
Major FY23 Outputs: | Develop comprehensive business requirements for enterprise IT Complete a systematic, full inventory of IT and data across enterprise. Draft strategic plan, and subsequent implementation after committee feedback.
Immediate Next Steps: | Test and refine the capability (gap) analysis process that will provide understanding of current state. Interview systems owners to understand current capabilities; interview and survey researchers and staff to understand business requirements; and conduct the capability (gap) analysis. Continue to work on other parts of the strategic plan, to include visualizing the future state. Continue to cultivate SOC forum to further open communication, receive feedback, and strengthen trust. Define requirements to conduct a full inventory of IT and data across the medical centers.
ORD Leadership Support Required to Accomplish Initiative Objective: | 
29

## Slide 30: FERSS
30

## Slide 31: FERSS: Objectives
Initiative Objectives: | Rollout tools to provide VA researchers and R&D offices with access to a wide range of short-term contracted research support resources (e.g., biostatisticians, study coordinators, home-visit nurses) needed to get critical research started or across the finish line more rapidly.
Outputs Listed: | FERSS Initiative has been fully rolled out to the field and includes: a request portal process for review and approval communication between ORD and vendor process deployment of contracted resources
31

## Slide 32: FERSS: Delivery Status
Outputs Delivered: | May 2021 – FERSS Contracting process began​ July 2021 – ORD Workgroups organized to address policy/procedures August 2021 – Project Manager engaged from Titan Alpha contract​ Sept 2021 – FERSS Contract awarded​ (contractor: Aptive HTG) Jan 2022 – Use cases piloted at 3 sites: Cleveland, Madison, and Portland ​ March 2022 – FERSS request SharePoint site launched​
Outputs Rescheduled: | None
Lessons Learned: | Biggest lesson learned involved the limitations in contractors accessing resources at the facility. This took initial negotiation and discussion on logistics and details with contractor. Workflows and processes were developed to address it and the process slightly altered from initial design. Engagement and planning with field input was invaluable.
Current Roadblocks: | None
Mitigation Strategies: | None
32

## Slide 33: FERSS: Proposed Next Steps
Recommendation for Initiative in FY23: | Based on current progress and experience, the initiative owner/sponsor’s recommendation for the future of the initiative: Continue the initiative into FY 23
Major FY23 Outputs: | Increase the number of stations utilizing FERSS Develop sustainment plan (i.e., budgeting model)
Immediate Next Steps: | List of immediate next steps initiative with take based on: Exercise option year 1
ORD Leadership Support Required to Accomplish Initiative Objective: | None at this point.
33

## Slide 34: Central Research HR Function
34

## Slide 35: Central Research HR Function: Objectives
Initiative Objectives: | Establish a central research HR team to efficiently manage research HR processes, classify positions, hire, and onboard qualified staff for VA Research projects, limiting research start-up and execution delays
Outputs Listed: | Primary output of establishing a Service Line Agreement was achieved in July 2022. However, this output will need to be redone.
35

## Slide 36: Central Research HR Function: Delivery Status
Outputs Delivered: | Primary objective was to obtain the Service Line Agreement (SLA)
Outputs Rescheduled: | While the SLA was signed, the implementation of the Pilot has been delayed. SLA will need to be re-negotiated Centralized HR processes will occur but in a different fashion
Lessons Learned: | Constant communication to local Human Resource Officers would have allowed for the successful implementation of the Pilot. Confirmation and possible ownership of parts can facilitate continual engagement. WOC implementation will be difficult due to variety of systems used to manage them.
Current Roadblocks: | Need for new SLA
Mitigation Strategies: | Continue to analyze and redefine the implementation. Consider implementation into two waves rather then 8. First wave will be all VA paid staff. Second wave will encompass WOC
36

## Slide 37: Central Research HR Function: Proposed Next Steps
Recommendation for Initiative in FY23: | Based on current progress and experience, the initiative owner/sponsor’s recommendation for the future of the initiative: Continue to negotiate and finalize SLA in FY 22 so that implementation of VA salaried staff transition occurs in 1st Quarter.
Major FY23 Outputs: | Milestone 1 - end of 1st qtr – Transfer all VA Research Paid staff to Centralized system Milestone 2 – end of 4th qtr- develop and implement plan for WOC transition
Immediate Next Steps: | List of immediate next steps initiative with take based on: Finalize negotiations of SLA
ORD Leadership Support Required to Accomplish Initiative Objective: | CRADO has been informed of delay. ORD leadership may need to discuss with VHA leadership the delays and may need to request meeting with operations leadership to further champion the transition. This activity should be delayed until mid September and the meeting should be pursued if there is no forward movement by WMC.
37

## Slide 38: Partnered Research Program
38

## Slide 39: PRP: Objectives
Initiative Objectives: | Implement streamlined and standardized clinical trial start-up activities for industry-sponsored multisite trials to expand Veterans’ access to high-quality clinical trials
Outputs Listed: | By April 30, 2022: PRP Strategic Plan (including budget, concept of operations, PRP office staffing and structure) Service specific SOPs Additional resources to support day-to-day operations Post trial start up evaluations By October 30, 2022: Staff to implement PRP functions Additional identified SOPs Detailed communication plan and feedback mechanism Deployed SAG
39

## Slide 40: PRP: Delivery Status
Outputs Delivered: | Service specific SOPs and email templates related to initial inquiries, centralized CDAs Creation of PRP webpage Development of Decision Tool/Guidance for External Partners interested in partnership. Development of Request for Collaboration form to streamline initial engagement Development and management of Inquiry Database, Project Database and Reporting tool to track and manage requests for collaboration and activity related to subsequent projects. Implementation of VAIRRS based centralized privacy review process for select multisite trials
Outputs Rescheduled: | Detailed communication plan and feedback mechanism* Additional resources to support day-to-day operations* Post trial start up evaluations Staff to implement PRP functions* Deployed Staff Administrative Guide (SAG)* PRP Strategic Plan* *Delivery of these outputs has been postponed to FY 2023 due to reconsiderations made by initiative owner based upon lessons learned.
40

## Slide 41: PRP: Delivery Status (continued)
Lessons Learned: | Some outputs initially proposed assumed that existing resources would be sufficient to meet completion goals. However, additional time and resources were required to address unanticipated foundational issues. Specifically: There was insufficient information available and/or heterogeneity regarding VA site and industry experience, challenges and best practices which required more effort to streamline and standardize start up activities. Stakeholders had broader expectations for PRP resulting in regular need to work with/communicate role and expectations. i.e., stakeholders expected PRP to now be free service to handle time intensive activities without consideration of primary scope. Lack of clarity around use of contractor support impeded ability to allocate various day-to-day PRP operational tasks to others. Communications by others created expectation that VA was more open for business and it was PRP’s role to handle it.
41

## Slide 42: PRP: Delivery Status (continued)
Current Roadblocks: | Resourcing/Strain on bandwidth of PRP Manager (and DCRADO-EO to an extent) to devote to initiative while managing majority of day-to-day activities for PRP in its current state (mailbox management, meetings, working with SPMs/clinical experts, CDAs, tracking, electronic filing, overseeing 2 pilot trials and activities of the contractor facilitator). This further complicated by the ongoing issue of contractor access/engagement in trials under the terms of VA CDAs and CRADAs.
Mitigation Strategies: | Awaiting formal opinion on contractor role/access from Office of General Counsel Request submitted for contractor support in the form of administrative support for mailbox management & electronic filing/tracking Request submitted for contractor support for Project Lead/Manager to assist Program Manager with Initiative activities.
42

## Slide 43: PRP: Proposed Next Steps
Recommendation for Initiative in FY23: | Revise outputs in response to lessons learned and better assessment of requirements to complete them Provide talking points to ORD and Field on PRP’s current capabilities/roles
Major FY23 Outputs: | Continue to identify existing tools and resources required to streamline/standardized key processes within each workstream Finalize Process Map defining the industry and researcher customer journeys (2 workstreams) and associated model(s) for partnership. Develop repository of existing tools and resources/FAQs VAIRRS based process for centralized Information Security Reviews. Develop Strategic Plan for PRP expansion including budget, concept of operations, staffing and structure
Immediate Next Steps: | Use contractor support to bring on Project Manager dedicated to Initiative efforts. Use contract mechanism to bring on PT support for PRP administrative tasks
ORD Leadership Support Required to Accomplish Initiative Objective: | Provide briefing to ORD leaders and have PRP provide talking points to ORD and Field on PRP’s current capabilities/roles to mitigate added duties and/or responsibilities
43

## Slide 44: Appendix: Organizational Alignment Roadmap
44

## Slide 45
 | Phase 0 Roadmap Development Phase Sept 1 – Sept 30 (4w) | Phase 1 End-state Org functions Phase Oct 1 – Nov 14 (6w)
Objectives | Kick-off org design team and set up the project for success Finalize detailed project roadmap | Identify gaps and pain points within the current org and process to design the future-state ORD. Establish statements for end-state ORD’s functions
Milestones | Establish project team Refine project scope and objectives Finalize detailed project roadmap Org design stakeholder list Develop project templates: roles charters, decision rights, functional statements, etc. Establish design principles Onboard the initiative team and ensure they understand their roles and responsibilities Ensure ORD staff is aware of the effort and understands its purpose Draft a Communication plan Benchmark leading research organization’s functions Employee engagement list: working group and committees list | Develop the “real” org chart Build excel “Scope of Control model” Map opportunities for improvement for the org structure, ORD research process, and functions Develop a draft statement of end-state ORD’s functions Finalize the Communication plan Engage the initiative team as well as ORD staff and leadership to validate the current org structure Validate and get input into the end-state organization functions with the leadership and the governance
Outputs | Initiative Overview and Roadmap Design principles and standards Stakeholder list Project templates | “Real” org chart (with Scope of Control (SoC) analysis) Org structure opportunity analysis End-state function statements Communication plan
Org design team Roadmap (page 1 of 2)
45

## Slide 46
 | Phase 2 L1 – L2 Design Phase Nov 15 – Jan 7 (8w) | Phase 3 L3 – L5 Design Phase Jan 8 - Mar 31 (3m) | Phase 4 Continued Implementation Phase April 1 – Sept 30 (3m to 6m)
Objectives | Start to design the layers of the org Develop L1 - L2 roles, responsibilities, decision rights | Continue to design each layer from top to bottom, ensuring collaboration mechanisms are in place. Develop L3 - L5 roles, responsibilities, decision rights | Working with WMC to approve org chart and PD’s Implementation
Milestones | Develop L1-L2 structure options Develop high-level L1-L2 roles and responsibilities Define L1-L2 decision rights OVIS (RACI equitant framework) Develop / confirm detailed position descriptions for L1-L2 Workshop peer review of L2 (final activity for L1 approval) Develop draft recruiting, staffing Notify L3 to L5 staff about their involvement in the design process and the role they are going to play in it Gather input from ORD leadership and the governance into the design of L1 and L2 | Develop L3 structure options A) Develop high-level L3 roles and responsibilities B) Define L3 decision rights OVIS (RACI equitant framework) C) Workshop to draft L3 charters D) Rule deviation charter review E) Workshop peer review of L3 by L2 – final activity before L1 approval Repeat steps A) to E) for L4 to L5 Develop mechanisms for collaboration and cooperation | Final org chart hand-off to WMC/HR Signed org chart Receive all PD’s Approved PD’s Begin recruitment Begin hiring
Outputs | Layer 1 & 2 org chart Layer 1 & 2 role charter Layer 1 & 2 decision rights Layer 2 Functional statement/charter Layer 1 & 2 analysis report | Plan for recruiting, staffing, and trainings Layer 3 to 5 org chart Layer 3 to 5 Role charter Layer 3 to 5 decision rights Layer 3 Functional statement/charter Layer 3 and 4 analysis report Final org chart | Signed org chart All new Position descriptions Signed position descriptions
Org design team Roadmap (page 2 of 2)
46

## Slide 47: Appendix: Actively Managed Portfolios Roadmap
47

## Slide 48: AMP Initiative Roadmap Overview
Phase 2: Discovery & Analysis
Phase 3: Plan Development
12/6 – 3/11
3/14 – 5/6
5/9 – 8/5
Phase 4: Implementation
8/8 – 10/14
Goals
Phase 5: Tracking and Evaluation
Ongoing
Phase 1: AMP Definition
  AMP charter
  AMP Leader Role Charter
  Gap Analysis of P.O.
  Communications Framework
  Change Champion materials
  P.O. Prioritized Action Plan
  AMP funding decision SOPs
  SOPs for rapid and program-directed peer reviews
  Inventory of needed dashboard functionality
Outputs
  P.O. funding autonomy
  Codified performance metrics to measure an AMP
  Portfolio Analysis Dashboard
  AMP progress reports on objective accomplishments
  -Monitor AMP performance and assess utility of collected data
  -Monitor composition balance of the portfolio
  -Standard reporting structure for AMP activities
  -Identify AMP Capability priorities for P.O. and improvement steps
  -Coordinate and prioritize funding for AMP research
  -Expedited review of priority proposals
  -Define dashboard capabilities
AMP: Actively Managed Portfolio
PO: Precision Oncology portfolio
SOP: Standard Operating Procedures
Indicates an Initiative-level objective has been achieved
We are here
  -Define purpose, requirements, and capabilities of an AMP
  -Determine role/responsibilities of an AMP leader
  -Complete inventory and understanding of current P.O. functions
  -P.O. has been granted oversight and authority of their own budget
  -P.O. implementing Prioritized Action Plan
  -Identify performance metrics to measure an AMP
  -Launch pilot to track/report AMP data
48
Notes: Phase 1:
*AMP Charter: describe unit’s mission, key activities, scope of control, relationships to other units.
Phase 2:
P.O. the maturity assessment/gap analysis/prioritization plan for Precision Oncology will reveal which resources currently exist that are required for an AMP as well as building out those not currently in existence (obviously certain resources will be funding process and metric dashboards already covered in other objectives but resources such as support personnel, etc would be coordinated with Org Design team)
Phase 3:
**Plan to mature the Precision Oncology Portfolio as an AMP is important b/c it is currently the most closely aligned research portfolio to an AMP. As referenced in the introduction to LHS model, the Precision Oncology portfolio has considerable experience developing certain critical structures to operate as a learning health system. Building off these existing structures in P.O. will not only provide critical abilities inside the portfolio, it will also reduce the time needed to fully develop the framework and structures of an Actively Managed Portfolio, hastening its adoption to other research portfolios of high importance to the veteran community.
Phase 4:
**Portfolio Analysis Dashboard: Potentially interactive graphs in PowerBI that pull research directly from VAIRRS, allowing the AMP leader to assess the corpus of research across given categories.
Phase 5:
**Funding composition targets refers to establishing an appropriate balance between portfolio directed and service directed funding levels for the portfolio
**Dates have been added instead of weeks per Rachel’s feedback.

## Slide 49: Appendix: Finance Process Roadmap
49

## Slide 50: Project Plan with proposed activities and status
Phase 3 – Iteration & Implementation
Phase 2 – Design & Development
Goals | Align with the client on project objectives | Understand existing processes and impact of current state | Synthesize Discovery findings to identify Field needs, and develop trainings to address | Determine requirements and develop v1 Reallocation process/tools | Establish formal processes for Q4 Reallocation; test v1 Reallocation tools | Pilot tools for Q4 and iterate for FY23; formalize Q1 processes to begin FY23
Activities | Set meeting cadence Review and synthesize background material Onboard team members Develop Roadmap with key milestones Secure Roadmap approval from Internal Ops subcommittee | Develop standard interview guide Setup and conduct 28 stakeholder interviews Synthesize findings Develop initial recommendations based on findings Map current state process Facilitate weekly working groups on select topics | Identify outstanding communications needs in Field Design communications platforms to address needs, including Finance landing page and calendar Determine high-level training requirements Establish monthly training cadence Determine specific monthly topics for FY22 and outline quarterly topics through FY23 | Compile initial criteria and draft initial reallocation frameworks (5/31) Map ideal state Q4 reallocation process (6/2) Map ideal state Q4 PMO and pullback process (6/14) Draft SOP of Q4 reallocation (6/30) Collect stakeholder feedback on reallocation criteria (6/23-30) Validate SOPs with stakeholders and update per feedback (7/15) Facilitate development of training materials | Review Reallocation criteria, framework, process and collect stakeholder inputs Field Survey Analysis FY 23 Quarterly & Monthly Thematic Training Plan Best Practice Document Template Best Practice Documentation: Outline and QA - FY22 Topics Share Point Landing Page Design Finance Communication Plan Process and incorporate Q3 RAFT data as available Monthly training materials | Conduct necessary RAFT analysis to support identification of high-risk projects Transition ownership of tools to Office of Finance Identify long-term owners of monthly trainings and transition ownership Support development of FY23 Initiative Objectives
Outputs | List of consistent interview questions Roadmap, OKRs | Interview synthesis Current process maps of station- and ORD-level fund management1,2,3 | Monthly training plan for FY221,2 Landing page requirements and wireframe mockup5 | v1 process SOP, proposal collection form, and evaluation criteria3,4 Monthly training materials1,2,5 | v1 Reallocation process and tools to support Q4 reallocation3,4 Monthly training materials1,2,5 | v2 processes and tools for FY233,4 AAR of Q4 Reallocation3,4 FY23 Training roadmap1,2,5
Oct – Dec 2021
Feb – Apr
Jan – Feb
Handoff for FY23
Design III – Communications
Design II – Reallocation
Design I – Trainings
Discovery
Roadmap
Aug - Sep
Apr – July 15
July 16 – Aug 26
Phase 1 – Discovery & Standup
Already complete
In progress
Not yet started
* Superscripts reflect relevant Initiative Objectives
50

## Slide 51: Finance Initiative Objectives: Status as of August 2022
Objective | Status
1. Improve station-level monitoring and tracking of project obligations, expenditures, and unobligated balances | Addressed directly through ongoing trainings, kicked off April 26 to continue through FY23 Completed 4 trainings with 77% audience satisfaction and good feedback as of July 25th Developed a thematic quarterly and monthly training plan based on field survey results for FY 23 Developing Best Practice resources for delivery by end of FY 22 (quick-wins) and provide more best practices throughout FY 23
2. Develop policies and procedures to obligate Prior Year funding by January each Fiscal Year | Draft policies for field implementation in FY 2023 Develop policy on 4% Carryover Monthly training and best practices will also support this objective
3. Develop processes, mechanisms, and policies to identify and reallocate funding | Being addressed through quarterly RAFT reports, standardizing the procedures for PMO, RAFT and Pull Backs in Q3 and Q4. More Development needed in FY 23
4. Establish reallocation criteria to inform recommendations to Service Directors and CORE | Being addressed through quarterly RAFT reports New UFR/SFR process pilots some practices for reallocation of funding at enterprise level Established criteria for reallocation of funds and drafted Score Card for proposal review More Development needed in FY 23
5. Establish clear lines of communication with key field stakeholders to ensure buy-in, understanding, and compliance | Addressed directly through ongoing trainings Further addressed through Initiative communications plan, centralized landing page Establishing a single end point-mail box for field questions and feedback
Objectives 1, 2, and 5 will be addressed in the short term through monthly trainings, which will continue into FY23
Objectives 3 and 4 (in blue) require a foundation of field training (monthly trainings and best practices) to be fully successful.
51

## Slide 52: Appendix: STEAM Roadmap
52

## Slide 53: Staff Development and Mentoring Initiative High-Level Roadmap and Goals
Goals | Establishing Vision and Mission statements Scoping Initiative and diagnosing the problem (problem statement) 1:1 Interviews and Focus Groups (with Past Participants) | Initiative Scoped Internal VA Resources and Gaps identified Data call for Interested Participants and VHA Mentors | Formalization of plan, timelines, and committed resources Contract awarded (if applicable) | Organized operations in place First pilot training group starting the training End State: SDM (Staff Development and Mentoring) training for participants underway
Goals | Develop roadmap Identify initiative team members Continue engaging with stakeholders to complete SLA negotiations Identify funding requirements and secure funding to fulfill SLAs Solidify annual SLA reevaluation timeline Define the roll-out waves Develop communications plan for pre-Wave 1 (RO’s and local payroll) Engage operations leadership to get buy in and support for the roll out |  |  | 
 | Develop Vision Statement |  |  | 
Phase 1: Data Collection and Scope
Nov 21 – Mar 22
Phase 2: Resource Development
Apr 22 – Jun 22
Phase 3: Formalization
Jul 22 – Sep 22
Phase 4: Initiation of Training
Oct 22 – Dec 22
  Completion of first pilot program
  Plan for second iteration
  Follow-on training in 2023 Calendar Year and long-term planning for field positions
Phase 5: Sustainment and Evolution
Jan 23
53
Notes: 5 Phases:
Each phase after Phase 1 aligns with the Corresponding FY Quarter

## Slide 54: Appendix: IT & Data Governance Roadmap
54

## Slide 55
Objective #1:
ORD has developed and implemented a strategic plan to organize the systems and their components across the research enterprise, which aligns with current and forecasted resources, policies, and ORD’s strategic priorities.
Objective #2:
ORD has established Standard Operating Procedures to support current policies and systems for both IT and Data, that ensure services and products are delivered consistently every time across the research enterprise.
Objective #3:
ORD has established IT and Data Governance to provide policy, strategy, best practices, coordination, and standards aligned with the VA and VHA Data Management Strategy.
IT and Data Governance Initiative: Timeline (Draft Roadmap Plan)
Objective
Specified Milestone
Implied Milestone
Phase 1:
Understanding and Assessment
Phase 5:
Implementation and Support
Phase 2:
Inventory and Analysis
Phase 4:
Plan Development
MS 1.2: Component inventory conducted & catalogued
    MS 3.1: Current governance & policies inventoried and reviewed
    MS 3.3: First set of new and updated policies published
MS 2.1: SOPs inventoried and reviewed
MS 2.2: First set of new and updated SOPs published.
MS 1.4:
Gap analysis completed
MS 1.6: ESC approved strategic plan
MS 1.3: Needs assessment (business requirements) done
MS 1.5: Draft strategic plan completed
    MS 3.2: Establish ORD Governance council
New Milestone
Goal: ORD has governance over a modernized, secure, collaborative system-of-systems with associated processes that increase capability and access for ORD staff and researchers to efficiently conduct and support research.
we are here
Future Objectives
Future objectives identified in strategic plan
MS 1.1: Initiative
(Mission) Analysis
<1-Oct-2021 | <1-Nov-2021 | <1-Dec-2021 | <1-Jan-2022 | <1-Feb-2022 | <1-Mar-2022 | <1-Apr-2022 | <1-May-2022 | <1-Jun-2022 | <1-Jul-2022 | <1-Aug-2022 | <1-Sep-2022 | <1-Oct-2022 | <1-Nov-2022 | <1-Dec-2022 | <1-Jan-2023 | <1-Feb-2023 | <1-Mar-2023 | <1-Apr-2023 | <1-May-2023 | <1-Jun-2023 | <1-Jul-2023 | <1-Aug-2023 | <1-Sep-2023
Main Effort: Strategy Development Process
55
Notes: UPDATES:
MS 1.2: Establish ORD Governance council
Moved from before strategic plan to after its approval anticipating that an office might be recommend to provide governance.
MS 1.4: Policy and rules recommendations prioritized and provided
Implied and included it MS 1.3 (First set of new and updated policies published)
MS 2.1: Initiative (Mission Analysis)
Add to capture the milestone completed
MS 2.3: Desired endstate developed
  Included it MS 2.5 (Draft strategic plan completed)
MS 2.7: Strategic plan implemented that aligns resources
  Implied and included in MS 2.6 (ESC approved strategic plan)
MS 3.2: IT & Data Team established, and initial process developed
  Deleted as it was not in updated Initiative guidance slide. Anticipate it will be part of draft Strategic Plan
MS 3.3: SOP gaps identified, prioritized, & recommendations made
Included it MS 3.2 (First set of new and updated SOPs published)

## Slide 56
Objective
Milestone
Phase 1:
Understanding and Assessment
Phase 5:
Implementation and Support
Phase 2:
Inventory and Analysis
Phase 4:
Plan Development
Future Objectives
<1-Oct-2021 | <1-Nov-2021 | <1-Dec-2021 | <1-Jan-2022 | <1-Feb-2022 | <1-Mar-2022 | <1-Apr-2022 | <1-May-2022 | <1-Jun-2022 | <1-Jul-2022 | <1-Aug-2022 | <1-Sep-2022 | <1-Oct-2022 | <1-Nov-2022 | <1-Dec-2022 | <1-Jan-2023 | <1-Feb-2023 | <1-Mar-2023 | <1-Apr-2023 | <1-May-2023 | <1-Jun-2023 | <1-Jul-2023 | <1-Aug-2023 | <1-Sep-2023
Operational Line of Effort (LOE) Continuing to support existing IT & data programs/projects. Ready to support new IT & data activities that are aligned with the anticipated ORD IT & data strategic plan and governance as that becomes clearer through the process of developing the ORD IT & data strategic plan.
Strategic Line of Effort (LOE)
Working on achievement of 3 objectives with the main effort being the development of an ORD IT & data Strategic Plan (Obj #1) that will take an enterprise approach for IT and data governance supported with processes provided by procedures (Obj #2) and policies (Obj #3).
ORD IT & Data
Strategic Plan
Key milestones for development of strategic plan:
MS 1.4:
Gap analysis completed
MS 1.2, 1.3, 2.1, 3.1: Systems, Policy, & SOP inventory and needs assessment completed.
MS 1.6: Committee approved strategic plan
MS 1.5: Draft Strategic plan completed
MS 1.1: Initiative (Mission) Analysis completed
ORD has governance over a modernized, secure, collaborative system-of-systems with associated processes that increase capability and access for ORD staff and researchers to efficiently conduct and support research.
MS 2.3,3.3: Start drafting & publishing SOPs & polices
MS 3.2: Establish governance
oversight
Future objectives identified in strategic plan
IT and Data Governance Initiative: Concept and Timeline
Initiative
Goal:
Merge existing IT & data programs/projects into alignment with new governance where possible & require new activities to in order to come into existence.
Assign responsibility to implement ORD IT & data strategic plan and to: oversee IT & data governance; provide functions that support an enterprise approach for IT and data; and merge existing and new programs/projects within new framework.
Updated
56

## Slide 57: Process & Anatomy of Strategic Plan
Strategy - a leader’s plan to use resources in a distinct way to achieve its preferred endstate with an understanding of the associated situation and risks.
Summarizing of steps, but not all inclusive
FORMAT OF STRATEGIC PLAN FOR
IT AND DATA GOVERNANCE
Step I: Mission Analysis (Sus: 26-Oct-2021)
Create a shared understanding of the leadership’s overall purpose, tasks, requirements, and time horizon for the strategic plan.
Step 2: Situational Awareness and Understanding (Sus: 17-Dec-2022)
Gather and examine information about key factors and conditions in the environment to assess, understand, and define the current state through conducting a capability gap analysis.
Inventory Governance (Policy) and SOPs. (Sus: 03-Oct-2022)
Inventory Systems and their components (Sus: 28-Oct-2022)
Understand community business requirements. (Sus: 28-Oct-2022)
Conduct capability gap analysis. (Sus: 16-Dec-2022)
Step 3: Framing the Desired Future (Sus: 31-Dec-2022)
Reflect on the state of the current situation and the requirements to develop a desired, but realistic endstate and supported by stated conditions (goals) that must be created to achieve it that overcome anticipated challenges.
Step 4: Strategic Approach (Sus: 20-Jan-2023)
Develop and describe a unified set of broad sequenced actions, namely objectives, that the organization must take to create the desired conditions (goals) thus the endstate.
Step 5: Resource & Risk Management (Sus: 03-Feb-2023)
Identify, assess, control and balance between resources and risks to prioritize objectives.
Step 6: Assessment (Sus: 17-Feb-2023)
Develop continuous plan to measure performance and effectiveness of activities to determine progress towards creating a condition and achieving an objective.
Step 7: Refine Draft (Sus: 1-Mar-2023)
Review and refine draft strategic plan for submission.
  Future State
    Describes the anticipated future and the desired future (Endstate) and conditions (goals) that define achievement of the strategy. Details how to leverage strengths to take advantage of opportunities and overcome challenges. Lists guiding principles.
  Current State
  Describes the current state of the ORD IT and Data environment, to include offered products and services (via systems); gaps in business requirements, policies, and SOPs; limitations to providing them; and strengths and weakness.
Introduction
    Describes ORD’s mission, vision, and priorities, and task to develop a strategic plan, its purpose, to include specified and implied requirements that need to be considered within the plan.
  Objectives and Solutions
  Provides and describes a set of clearly defined, decisive, and attainable goals (objectives) that are measurable and time-bound to move towards a stated condition(s); and can provides actionable solutions to meet achieve those objectives.
  Resources and Risks
    Describes the resources required needed to support the objectives; and describes the risk of failure or unacceptable consequences in taking, or not taking, a specific objective.
  Assessment
    Describes the Measures of Effectiveness (MOE) that indicate a change of the state of the environment over time (conditions) to assess if we doing the right things; and describes the Measures of Performance (MOP) that indicate progress towards achieving an objective over time to assess if we are doing things right.
We are Here
57

## Slide 58: System-of-Systems: Framework for understanding environment
Area of Operations
Concept illustrates the multitude of systems in ORD’s area of operations that it organizes represented by their function type (not all inclusive).
System by Function
Infrastructure
Tools
Data
Services
System
Components
Coordination by ORD
ORD Initiative Team
System Owner Coordination (SOC) group
A system: A working combination of some, or all, components of infrastructure, tools, data, and support services under direct management that provides the capability to conduct research.
System-of-Systems (SoS): A collection of systems that support research, each capable of independent operation, that when organized together achieve additional desired research capabilities.
Function: A set of related processes or activities carried out by a group.
Quantitative Analysis Systems
Finance Systems
Regulatory Systems
Patient Registry Systems
Basic / Wet Lab Systems
Field-based Research Systems*
Biomedical Systems
Veterinary Research Systems
Academic Affiliate Systems*
Clinical Trial Systems
Qualitative Analysis Systems
Multi-year Planning, Programming, Budgeting, and Execution (PPBE) Systems
Other Research Administration Systems
Data Repository Systems
Biorepository Systems
Grant Management Systems
58
Notes: To facilitate the process to develop a strategic plan focused on governance, we developed a framework to help us better understand the connectedness of the wider IT and & data research structure.
We decided on the term System-of-Systems (SoS), which we define as a collection of systems that support research, each capable of independent operation, that when organized together achieve additional desired research capabilities.
We define an individual system as a working combination of some, or all, components of infrastructure, tools, data, and support services under direct management control that provide the capability to conduct research.
This framework will allow us to focus inventories to increase our understanding of the environment, develop goals and objectives from an ORD IT and data perspective, and work collectively to provide more capability and capacity, and ultimately strengthen the potential impact that ORD research has.
Component Definitions:
Data: An elementary description of things, events, activities, and transactions derived directly or indirectly from patients or human research subjects that are recorded, classified, and stored, but not organized to convey any specific meaning. Data items can be numeric, alphabetic, figures, sounds, or images
Infrastructure: The processing, storage, networks, operating systems, and other fundamental computing resources that provides the user the ability to deploy and run tools to conduct research.
Support Services: A mechanism that can be accessed by users to support the use of one or more tools, data, and system to enable research.
Tools: Something, such as a commercially purchased or internally developed software, that allows users to perform a particular activity for research.
Systems Descriptions
Quantitative Analysis:
Qualitative Analysis:
Wet lab:
Biomedical (Plugged into scientific equipment):
Patient Registry:
Data Repository:
Biorepository:
Clinical Trial:
Finance:
Grant Management: Includes Merit Review.
Research Administration (other):
Veterinary (animal research):
Regulatory:
Multi-year Planning, Programming, Budgeting and Evaluation (PPBE) Strategic Management: The PPBE process is VA’s multi-year resource allocation process. Planning establishes the strategic priorities and required capabilities. Programming identifies and allocates the resources to the programs that will provide the capabilities. Budgeting develops the budgets and operating plans and provides justification for the approved programs. Execution involves developing and delivering the required capabilities to achieve the goals and objectives as well as evaluating if the outcomes.
  Includes Contracts
  Inlcuedes ATOs: VA distributes Authority to Operate (ATO) clearances to business partners to give them a “green light” to develop systems, products, and processes intended for use at VA. All VA information systems, including the system of the Contractor, must receive ATOs and complete other security requirements. This is a requirement to appropriately ensure the sensitive information of Veterans is appropriately protected.
Field-based Research:
Academic Affiliate:
Cross-functional activities for each system:
Policy and Plans: Orchestration of procedures and policy implementation
Concierge: help desk, guide, training/education, intersystem support

## Slide 59: Appendix: FERSS Roadmap
59

## Slide 60: Centralized Field Support Contract High-Level Roadmap
Phase 1: Develop & Plan
4 Weeks
12 Weeks
Phase 2.A: Implementation Activities
Quarterly
Phase 2.B: Assess Implementation
Develop the tools to enable researchers to access the centrally managed contract Develop communication and deployment plans to ensure success of the initiative Verify portal viability |  | Deploy centralized contract tool Deliver contractual staffing resources to the field |  | Assess effectiveness of implementation Take action to address issues
Request fulfillment SOPs Intake portal Implementation plan Communications & engagement strategy |  | Deployed portal and SOPs Feedback results Revised portal and SOPs |  | Feedback results Revised portal and SOPs Quarterly Implementation Assessment
SOP Development Define intake requests Define prioritization Define request execution Develop intake portal Pilot intake portal Revise intake portal Develop feedback plan and mechanisms Develop deployment/implementation plan Develop communications & engagement strategy |  | Deploy intake portal to field Communicate deployment to field Collect and analyze feedback & key metrics from the field Incorporate feedback into SOPs/Portal/Deployment plan Communicate changes to field |  | Collect feedback from field via feedback mechanism and on ad hoc basis Incorporate feedback into SOPs/Portal/Deployment plan Communicate changes to field
Goals
Milestones
Outputs
60

## Slide 61: Centralized Field Support Contract High-Level Roadmap
Q4 FY22
Phase 3: Contract Evaluation
Goals
Milestones
Outputs
4 weeks
Phase 4: Future State Analysis
Determine contract continuation course of action Adjust tools and processes to support course of action |  | Develop an understanding of the potential for the contract to be used for other resourcing needs
Contract evaluation determination |  | Findings from long term analysis
Develop contract continuity options End, Revise, Continue (largely) as-is Determine contract execution option Communicate determination Adjust SOPs to new contract environment |  | Conduct long term financial analysis of progress Finalize evaluation of potential contract expansion to other usages Analyze user feedback
61

## Slide 62: Appendix: Central Research HR Function Roadmap
62

## Slide 63: Central Research HR Function High-Level Roadmap
Goals | Establish agreements and secure funding to establish Central Research HR Function Get buy-in from operations leadership | Develop tools and guidance for implementation Plan the roll-out | Implement Central Research HR Function at the Wave 1 site Prepare for implementation at Wave 2-8 sites | Implement Central Research HR Function across the Research Enterprise
Activities | Develop roadmap Identify initiative team members Continue engaging with stakeholders to complete SLA negotiations Identify funding requirements and secure funding to fulfill SLAs Solidify annual SLA reevaluation timeline Define the roll-out waves Develop communications plan for pre-Wave 1 (RO’s and local payroll) Engage operations leadership to get buy in and support for the roll out | HR team hires/onboards staff HR team develops transition worksheet Communicate the roll out plan across the enterprise Identify staff to serve on the implementation team for the Wave 1 site Engage with staff at Wave 1 site Payroll at local sites Research offices Train local staff at Wave 1 site Develop template research site instructions Develop feedback mechanisms Design implementation tracking tool | Implement Wave 1 Recode all affected personnel Deploy tracking tool Update implementation strategy as needed Identify implementation team at Wave 2 stations and begin working with them to prepare for roll-out Engage stakeholders at Wave 2 sites Train staff at Wave 2 site Gather and analyze Wave 1 feedback Collect and track key metrics from Wave 1 site | (Repeat for all phases) Roll out at Wave 2-8 stations HR evaluates resource needs Train local staff Recode all affected personnel Identify and execute on improvement opportunities Engage key stakeholders as needed Update implementation tracking tool regularly Identify implementation team at Wave 2-8 stations and begin working with them to prepare for roll-out
Outputs | HR funding for initiative staff Signed SLAs Communications Plan Comms letter from operations leadership to site | Draft site SOPs for Wave 1 Local staff training materials Implementation team rosters HR worksheet Hired HR staff Feedback mechanism | Implementation tracking tool First wave of transitioned staff Updated transition SOPs Report progress to SC Initial access to CHRF resource at Wave 1 site | Active Implementation dashboard Incorporate feedback into active phases Access across the Research Enterprise to CHRF resources
Phase 1: SLA Negotiation & Committee Standup
Nov. – Dec.
Phase 2: Pre-Wave 1
Jan. – Feb.
Phase 3: Wave 1
Feb.
Phase 4: Implementation for Subsequent Waves
Mar. – Oct.
63

## Slide 64: Appendix: Partnered Research Program Roadmap
64

## Slide 65: Enhanced Partnered Research Program High-Level Roadmap
  Define EPRP Scope and Functions
  Outline the industry and researcher customer journeys
  Develop PRP service process SOPs
  Define team requirements
    Define staffing needs
    Obtain approval and funding for additional staff to support day-to-day operations
  Develop PRP budget estimates
  Identify and engage key stakeholders
  Develop communications plan
  Continue conducting pilot trials and conduct post-trial start up evaluations
  Identify additional SOPs that need to be developed
  Deploy SAG (EPRP team toolkit)
  Hire and onboard staff to implement PRP functions
  Deploy communications plan
  Develop additional SOPs identified during pilot trial and initial SOP development
  Continue engaging key stakeholders
  Develop standardized feedback mechanisms (internal survey) for industry partners and researchers for future use
  Deploy and refine standardized tools
  Identify and execute on improvement opportunities
  Gather and analyze feedback form customers
  Reevaluate the scope of operations and make a decision re. potential expansion of the Program
  If applicable, develop an expansion plan and obtain approval / funding
Phase 1: Infrastructure
Phase 2: Implementation
Phase 3: Innovation
Milestones
  EPRP Strategic Plan (including budget, concept of operations, PRP office staffing and structure)
  Service specific SOPs
  Additional resources to support day-to-day operations
  Post trial start up evaluations
  Staff to implement EPRP functions
  Additional identified SOPs
  Detailed communication plan and feedback mechanism
  Deployed SAG
  Updated Phase 2 tools
  Customer feedback analysis
  Expansion assessment report
  If applicable, funding request
Outputs
7 mo.
6 mo.
3 mo.
Goals
  Successful standup of more robust EPRP
  Continue development and procurement of tools and resources
  Raise internal and external awareness about the EPRP
  Assess sustainability of initiative progress and whether expansion is feasible/necessary
  Sustain operations and incorporate improvements
What other services/resources should I engage to ensure that I properly define what the PRP should encompass?
  Develop strategy, formalize processes, and define the scope of the EPRP
  Engage key stakeholders
  Secure staffing and resources
65