## Slide 1: Update on Psychedelic Assisted Treatment for Mental Health
Presentation for: USH Small Group
Presented by: Ilse Wiechers & Wendy Tenhula
Date of briefing: 07/24/2024
VETERANS HEALTH ADMINISTRATION
Draft - Pre-Decisional Deliberative Document
Internal VA Use Only

## Slide 2: Readiness to Launch VA Psychedelic Assisted Therapy
Five phases must occur before VA can begin providing MDMA-AT in clinical care settings*
Communicate
detailed-level
VA plan
Prepare for implementation
Training protocols
Certified healthcare setting criteria
Manufacturer Guidance
2
Establish
high-level implementation plan including
Research strategy
Safety criteria
Training plan
Phased roll-out plan
Planning for FDA Decision
Communicate
high-level
VA strategy
Refine implementation plan
Risk Evaluation and Mitigation Strategies (REMS)
Label Requirements
FDA Decision
1
Communicate
medium-level
VA strategy
Refine implementation plan
Drug moved to different schedule
Possible additional controls
DEA Guidance
& State Reschedule
3
Communicate medium-level
VA strategy
Refine implementation plan
Safety monitoring processes created
Added to VA Formulary
VA PBM Process
4
Communicate readiness
Final preparation for implementation
Training
Site walk-through
Readiness checklist
Site review
Phased roll-out plan
Readiness Verification & Final Prep to Launch
5
Timing: Potentially expected August 2024
Timing: 90 day window for DEA guidance, then states will reschedule
Timing: 90 day window after DEA guidance
Timing: 0-60 day window after FDA decision
Timing: 30-60 day window after step 4
Launch & Beyond
Communicate VA MDMA-AT Launch
Begin phased launch at initial sites
Progressively expand services to more VA facilities based on need, safety, site readiness, and drug availability
Sequence of Phases
4
5
Earliest Launch
February 2025
1
3
VA is ready to see the first patient!
2
DRAFT – Internal VA Use Only
*Timeline reflects FDA approval. Without approval, the timeline ends at Step 1

## Slide 3: Psychedelic Assisted Therapy Updates
IPT Updates
Drs. Wiechers and Tenhula participated in a CMS Grand Rounds panel on 7/9
15Ops memo announcing IPT released 7/10
Re-scheduled training session to 7/23 with Lykos for IPT members to enhance understanding of treatment modality
Executive Steering Committee planning Face-to-Face for 8/27-8/28 to accelerate work following FDA decision
Lykos Therapeutics Updates
Lykos is revising treatment manual and training materials with anticipated finalization date in the fall (after REMS and label requirements released)
Lykos is preparing for a commercial launch anticipated in early 2025
Agreement to customize training program for VHA providers
Draft - Pre-Decisional Deliberative Document
Internal VA Use Only

## Slide 4: Current Psychedelics Research in VA (Externally Funded)
There are multiple studies funded by external sources being conducted with Veteran participants at VA Medical Centers.
*As of 6/11/2024
Site | MDMA |  | Psilocybin | 
Site | Active | Complete | Active | Complete
Albany, NY | 0 | 1 | 0 | 0
Bronx, NY | 1 | 0 | 0 | 0
Loma Linda, CA | 1 | 0 | 0 | 0
Los Angeles, CA | 1 | 0 | 0 | 0
Palo Alto, CA | 1 | 0 | 1 | 0
Portland, OR | 1 | 1 | 1 | 1
San Diego, CA | 2 | 0 | 0 | 0
San Francisco, VA | 2 | 0 | 3 | 0
Phoenix, AZ | 0 | 0 | 1 | 0
West Haven, CT | 0 | 0 | 5 | 0
Notes: Studies Under Review / In Planning are not public domain; however are as follows:
MDMA: 6 studies at 5 sites
Psilocybin: 2 studies at 3 sites

## Slide 5: Launch of VA Funded Research
First deadline for submission of pre-applications closed 4/1
  21 of 31 pre-applications accepted
  6 submissions accepted for first deadline for scientific proposals; anticipate more submissions at next deadline
Announcement of funding decisions will occur on a rolling basis, beginning in late August/early September
ORD staff will work with Principal Investigators to accelerate start-up

## Slide 6: Next Steps
VHA Psychedelic Assisted Therapy IPT
Sequester to accelerate review/adoption of REMS/label requirements 8/27-8/28 in DC
Continue providing monthly updates to VA as part of Departmental strategic initiative
Continue engagement with Lykos team to support roll out of MDMA-AT (if approved)
Stand up Community Care Workstream to progress on deliverables to establish a community care pathway for MDMA-AT
Produce draft eligibility criteria and prioritization plan for VA enrollment in MDMA-AT treatment
Identify potential lead implementation sites for initial roll out